## Raw Data
Aura Motion — Client Projects Export ¦ 2024 Full Year ¦ Exported: 15-01-2025
Project ID | Client Name | Project Type | Start Date | Deadline | Actual Delivery | Budget (€) | Invoiced (€) | Status | Lead Designer | Hours Logged
| Urban Eats | Social Content Package | 2024-04-05 | 5 Jun 2024 | 05.06.2024 | 4500 | € 2250.00 | Invoiced | Priya K. | 11 hours
AM-2402 | Bloom Cosmetics | Explainer Video | February 5, 2024 | 03-28-2024 | 2024-03-28 | 2400 | €2400.00 | Invoiced | Sam A.
AM-2403 | NovaPay | Training Video | 14.08.2024 | 17.09.2024 | 27 Sep 2024 | 2400 |  | Completed | priya k. | 15 hours
AM-2404 | Bloom Cosmetics | BRAND ANIMATION | 16.01.2024 | 28/02/2024 | February 28, 2024 | 3200 | 3200.00 EUR | completed | YUKI | 118.0
AM-2405 | Modo Fashion | Explainer video | 06.06.2024 | 28.07.2024 | 07-28-2024 | 9500.00 EUR | 4750,0 | on hold | Priya | 17
AM-2406 | TechFlow GmbH | Training Video | 8 Mar 2024 | 28.03.2024 |  | 6800 | €5100.00 | Cancelled | sam a. | 65
AM-2407 | Bloom Cosmetics | social content | 5 Jun 2024 | 07-19-2024 | 19.07.2024 | 7800.00 | EUR 7800.00 | Invoiced | Priya K. | 17
AM-2408 | Modo Fashion | Explainer Video | 2024-09-24 | 28.09.2024 |  | 4500.00 | 4500.00 EUR | On Hold | Sam A. | 13.0
AM-2409 | TechFlow GmbH | Traning Video | 05-13-2024 | 2024-06-25 | 06-28-2024 | 1500 | 1500.00 | Invoiced | Yuki T. | 92 hours
AM-2410 | NovaPay | Brand Animation | 2024-02-10 | 2024-03-28 | March 28, 2024 | 9500 | EUR 7125.00 | Cancelled | YUKI | 54h
AM-2411 | Solaris Energy | Brand Animation | May 4, 2024 | 06-22-2024 | 2024-06-22 | 1500 | 1500.00 EUR | Invoiced | Yuki T. | 60h
AM-2412 | Modo Fashion | Brand Animation | 10 Apr 2024 | 26/05/2024 | 28 May 2024 | 9500 | 9500,0 | In Progress | Yuki T. | 90
AM-2413 | Urban Eats | BRAND ANIMATION | 09.03.2024 | 2024-04-23 | 23.04.2024 | 3200 | 3200.00 | Cancelled | Priya | 55 hours
AM-2414 | TechFlow GmbH | social content | 05-16-2024 | 18/07/2024 | 2024-07-23 | € 7800.00 |  | Invoiced | YUKI | 38
AM-2415 | NovaPay | Social Content Package | 20 Aug 2024 | 28/09/2024 | 2024-09-28 | 4500 | € 3375.00 | Cancelled | Sam A. | 16
AM-2416 | TechFlow GmbH | Social content package | August 2, 2024 | 09-28-2024 | 28.09.2024 | 9500 |  | Completed | Priya | 77h
AM-2417 | Urban Eats | explainer video | 03.03.2024 | 05-06-2024 | 06.05.2024 | 1500.00 |  | Invoiced | sam a. | 44
AM-2418 | Solaris Energy | Social Content Package | 2024-08-13 | September 20, 2024 | 25/09/2024 | 7800 | € 7800.00 | cancled | Yuki T. | 21 hours
AM-2419 | TechFlow GmbH | Explainer Video | 2024-08-02 | October 6, 2024 | 28/10/2024 | 1200 | EUR 1200.00 | Invoiced | Yuki T. | 116
AM-2420 | Kira Health | BRAND ANIMATION | 19/07/2024 | 28.07.2024 |  | 3200 | € 3200.00 | ON HOLD | Sam Adler | 11
AM-2421 | Urban Eats | Brand Animation | August 7, 2024 | September 28, 2024 | September 28, 2024 | €7800.00 | 5850.00 | Cancelled | Priya | 78
AM-2422 | NovaPay | Brand Animation | 17 Jun 2024 | 17/07/2024 | 17 Jul 2024 | 4500.00 EUR | €3375.00 | Invoiced | Yuki T. | 16.0
AM-2423 | NovaPay | Brand Animation | June 21, 2024 | 2024-06-28 | 28 Jun 2024 | 7800 | € 7800.00 | in progress | YUKI | 114h
AM-2423 | NovaPay | Brand Animation | June 21, 2024 | 2024-06-28 | 28 Jun 2024 | 7800 | € 7800.00 | in progress | YUKI | 114h
AM-2424 | Modo Fashion | Traning Video | 10/09/2024 | 28/09/2024 | 28/09/2024 | 4500.00 EUR | € 4500.00 | cancled | Yuki T. | 100
AM-2425 | NovaPay | Event Reel | 10-09-2024 | 11-28-2024 | 28 Nov 2024 | 1200 |  | Cancelled | priya k. | 46
AM-2426 | Kira Health | BRAND ANIMATION | 2024-10-05 | 11.11.2024 | 28/11/2024 | 9500 | €9500.00 | On Hold | sam a. | 14.0
AM-2427 | TechFlow GmbH | social content | 7 Jun 2024 | 28/06/2024 | 28 Jun 2024 | 7800 | € 7800.00 | cancled | Priya | 71
AM-2428 | Bloom Cosmetics | Social Content Package | 05/07/2024 | 08-07-2024 | 2024-08-28 | 1200 | 1200.00 | Complted | sam a. | 113
AM-2429 | Solaris Energy | training video | 18.06.2024 | 27 Jul 2024 | 2024-07-28 | 4500.00 | 4500.00 EUR | Invoiced | sam a. | 25 hours
AM-2430 | NovaPay | Traning Video | September 18, 2024 | 28 Oct 2024 | 10-28-2024 | 6800 | 6800.00 | Completed | sam a. | 81
AM-2431 | TechFlow GmbH | Brand Animation | 07-05-2024 | 06.09.2024 | 09-16-2024 | € 1500.00 |  | Cancelled | sam a. | 98h
AM-2432 | Modo Fashion | Event Reel | 18.08.2024 | 25.09.2024 | 25.09.2024 | 9500 | 9500.00 EUR | on hold | Sam Adler | 48
AM-2433 | NovaPay | training video | September 13, 2024 | 24 Oct 2024 | 28.10.2024 | 3200 | 3200.00 | Cancelled | priya k. | 42
AM-2434 | GreenWave Solar | Event Reel | January 22, 2024 | 28/02/2024 | 28/02/2024 | 4500 | 2250.00 | invoiced | Yuki T. | 69
AM-2435 | TechFlow GmbH | Traning Video | 02-21-2024 | 2024-03-28 | 03-28-2024 | 1500.00 | 1125,0 | on hold | Priya K. | 85 hours
AM-2436 | Kira Health | Event reel | 2024-08-09 | 2024-08-28 | 28/08/2024 | €9500.00 | EUR 7125.00 | Invoiced | priya k. | 113
AM-2437 | TechFlow GmbH | Event Reel | 01.04.2024 | 03.05.2024 |  | EUR 4500.00 | € 4500.00 | In Progress | Priya K. | 47 hours
AM-2438 | Modo Fashion | Training Video | 05/04/2024 | 21 May 2024 | 05-26-2024 | 7800 | € 7800.00 | In Progress | priya k. | 119
AM-2439 | TechFlow GmbH | Event Reel | September 17, 2024 | 28.09.2024 | September 28, 2024 | 3200 | € 2400.00 | Completed | sam a. | 24
AM-2440 | Kira Health | Explainer video | 07-09-2024 | 07-23-2024 | 28/07/2024 | 2400.00 | 1200,0 | On Hold | YUKI | 106
AM-2441 | Kira Health | Event Reel | 2024-07-13 | 07-28-2024 |  | 3200 | 3200.00 | Completed | Priya K. | 94
AM-2442 | Arthaus Berlin | Brand Animation | 07/05/2024 | 2024-07-11 | 11/07/2024 | 1500 | 1500.00 EUR | cancled | Priya K. | 39
AM-2443 | Bloom Cosmetics | Social Content Package | May 8, 2024 | July 12, 2024 | 2024-07-07 | 9500 | 9500.00 EUR | Cancelled | priya k. | 15
AM-2444 | Modo Fashion | Brand Animation | 2024-08-02 | 10.09.2024 | 28 Sep 2024 | 9500 | 9500,0 | On Hold | Yuki T. | 79
AM-2445 | Modo Fashion | Social Content Package | February 15, 2024 | 24/03/2024 | 24/03/2024 | 4500 | € 2250.00 | cancled | priya k.
AM-2446 | Urban Eats | Event Reel | 08.08.2024 | 10.10.2024 | 10-05-2024 | 4500 | €4500.00 | On Hold | Sam Adler | 67.0
AM-2447 | Bloom Cosmetics | Social Content Package | 10-08-2024 | 10-28-2024 | 2024-10-28 | 6800 | 6800.00 EUR | cancled | priya k. | 40
AM-2448 | Modo Fashion | Explainer Video | 06/06/2024 | 28 Jun 2024 |  | 7800 | 5850.00 EUR | Completed | Priya K.
AM-2449 | Arthaus Berlin | Explainer Video | 16 Oct 2024 | 16.12.2024 | December 16, 2024 | 1500.00 EUR | 750.00 EUR | Completed | YUKI | 21
AM-2450 | Bloom Cosmetics | Event Reel | 05-13-2024 | 05-28-2024 | 28.05.2024 | 1200 | 1200.00 EUR | Completed | Sam A. | 78
AM-2451 | Arthaus Berlin | Training Video | June 19, 2024 | 06-28-2024 | 28 Jun 2024 | 1500 | €1125.00 | COMPLETED | Sam Adler
| Urban Eats | explainer video | 06.05.2024 | 06-28-2024 | June 28, 2024 | 1200 | € 1200.00 | On Hold | Priya K. | 115.0
AM-2453 | TechFlow GmbH | Explainer video | 06-18-2024 | 28.07.2024 | 28.07.2024 | 3200 | EUR 3200.00 | Completed | Sam Adler | 102 hours
AM-2454 | Bloom Cosmetics | Brand Animation | 2024-02-05 | 24 Feb 2024 |  | 1200 | 1200.00 EUR | Invoiced | Priya | 45
AM-2455 | NovaPay | Event Reel | 07-06-2024 | 28.07.2024 | 07-28-2024 | € 6800.00 | 6800,0 | On Hold | Sam Adler | 84